## Project Plan and Gantt
Project Name | quản lí cung cấp bưu thiếp
Project Manager | Nguyễn Thành Thiên + Đỗ Thanh Thảo
Project Deliverable | 17/10/2016
Scope Statement: | eclipse + SQL- server
Start Date | 2016-08-19
End Date | 2015-10-10
Overall Progress | 10%
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | Nguyễn Thành Thiên + Đỗ Thanh Thảo | 2016-08-24 | 2016-08-24 | 1 | Complete
Agree on objectives | Nguyễn Thành Thiên + Đỗ Thanh Thảo | 2016-08-24 | 2016-08-24 | 1 | Complete
Detailed Reqs. | Nguyễn Thành Thiên + Đỗ Thanh Thảo | 2016-08-27 | 2016-09-02 | 6 | Overdue
Techincal Reqs. | Nguyễn Thành Thiên + Đỗ Thanh Thảo | 2016-09-02 | 2016-02-09 |  | Not started
DB Development | Trần Minh Trung | 2016-08-19 | 2016-08-24 | 5 | Not started
Connect DB | Trần Minh Trung | 2016-08-19 | 2016-08-25 | 6 | Not started
Insert/Update/Query | Trần Minh Trung | 2016-08-19 | 2016-08-26 | 7 | Not started
API Development | Trần Minh Trung | 2016-08-19 | 2016-08-27 | 8 | Not started
Function 1 | Trần Minh Trung | 2016-08-19 | 2016-08-28 | 9 | Not started
Function 2,… | Trần Minh Trung | 2016-08-19 | 2016-08-29 | 10 | Not started
UI Client | Trần Minh Trung | 2016-08-19 | 2016-08-30 | 11 | Not started
Testing | Trần Minh Trung | 2016-08-19 | 2016-08-31 | 12 | Not started
Dev. Complete | Trần Minh Trung | 2016-08-19 | 2016-09-01 | 13 | Not started
Hardware Config. | Trần Minh Trung | 2016-08-19 | 2016-09-02 | 14 | Not started
System Testing | Trần Minh Trung | 2016-08-19 | 2016-09-03 | 15 | Not started
Launch |  | 2016-10-10 | 2016-10-10 | 0

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address
Nguyễn Thành Thiên | Team leader, Developer | 1. Make the plan of the project. 2. Assign task for your member. 3. Design GUI/database. 4. Code. 5. Write document | Skythiennguyen@gmail.com
Đỗ Thanh Thảo | Project Manager, Developer | 1. Design GUI/database. 2. Code. 3. Test 4. Analysis & design the system. | thanhthao1171996@gmail.com
n

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team